## ISO Conformance tests
Test / Number				Test Name	Test Class name	Status				Number of Frames in the test
							New API	New Run function	Wired AND Enabled		Notes	ISO note
Valid Frame Format – Received Frame
7	1	1		Identifier and number of data test in base format	TestIso_7_1_1	Completed	Yes	Yes		125					10
7	1	2		Identifier and number of data test in extended format	TestIso_7_1_2	Completed	Yes	Yes		125					10
7	1	3		Reception after arbitration lost	TestIso_7_1_3	Completed	Yes	Yes		10
7	1	4		Acceptance of non-nominal bit in base format frame	TestIso_7_1_4	Completed	Yes	Yes		1
7	1	5		Acceptance of non-nominal bit in extended format frame	TestIso_7_1_5	Completed	Yes	Yes		10
7	1	6		Protocol exception behaviour on non-nominal bit	TestIso_7_1_6	Completed	Yes	Yes		4
7	1	7		Minimum time for bus idle after protocol exception handling	TestIso_7_1_7	Completed	Yes	Yes		6		Ambiguous
7	1	8		DLC greater than 8	TestIso_7_1_8	Completed	Yes	Yes		7
7	1	9		Absent bus idle — Valid frame reception	TestIso_7_1_9	Completed	Yes	Yes		2
7	1	10		Stuff acceptance test in base format frame	TestIso_7_1_10	Completed	Yes	Yes		20
7	1	11		Stuff acceptance test in extended format frame	TestIso_7_1_11	Completed	Yes	Yes		18
7	1	12		Message validation	TestIso_7_1_12	Completed	Yes	Yes		1					15
Error Detection – Received Frame
7	2	1		Bit error in data frame	TestIso_7_2_1	Completed	Yes	Yes		1
7	2	2		Stuff error for basic frame	TestIso_7_2_2	Completed	Yes	Yes		99
7	2	3		Stuff error for extended frame	TestIso_7_2_3	Completed	Yes	Yes		178
7	2	4		Stuff error for FD frame payload bytes	TestIso_7_2_4	Completed	Yes	Yes		1008
7	2	5		CRC error	TestIso_7_2_5	Completed	Yes	Yes		9	TODO
7	2	6		Combination of CRC error and form error	TestIso_7_2_6	Completed	Yes	Yes		3
7	2	7		Form error in data frame at “CRC delimiter” bit position	TestIso_7_2_7	Completed	Yes	Yes		1
7	2	8		Form error at fixed stuff bit in FD frames	TestIso_7_2_8	Completed	Yes	Yes		22		Ambiguous
7	2	9		Form error in data frame at “ACK delimiter” bit position	TestIso_7_2_9	Completed	Yes	Yes		2
7	2	10		Form error in data frame at “EOF”	TestIso_7_2_10	Completed	Yes	Yes		5
7	2	11		Message non-validation	TestIso_7_2_11	Completed	Yes	Yes		1
Error frame management - Received Frame
7	3	1		Error flag longer than 6 bits	TestIso_7_3_1	Completed	Yes	Yes		3
7	3	2		Data frame starting on the third bit of intermission field	TestIso_7_3_2	Completed	Yes	Yes		1
7	3	3		Bit error in error flag	TestIso_7_3_3	Completed	Yes	Yes		3
7	3	4		Form error in error delimiter	TestIso_7_3_4	Completed	Yes	Yes		3
Overload frame management - Received Frame
7	4	1		MAC overload generation during intermission field	TestIso_7_4_1	Completed	Yes	Yes		4
7	4	2		Last bit of EOF	TestIso_7_4_2	Completed	Yes	Yes		4
7	4	3		Eighth bit of an error and overload delimiter	TestIso_7_4_3	Completed	Yes	Yes		4
7	4	4		Bit error in overload flag	TestIso_7_4_4	Completed	Yes	Yes		6
7	4	5		Form error in overload delimiter	TestIso_7_4_5	Completed	Yes	Yes		6
7	4	6		MAC overload generation during intermission field following an error frame	TestIso_7_4_6	Completed	Yes	Yes		4
7	4	7		MAC overload generation during intermission field following an overload frame	TestIso_7_4_7	Completed	Yes	Yes		4
Passive error state - Received Frame
7	5	1		Passive error flag completion test 1	TestIso_7_5_1	Completed	Yes	Yes		12
7	5	2		Data frame acceptance after passive error frame transmission	TestIso_7_5_2	Completed	Yes	Yes		4
7	5	3		Acceptance of 7 consecutive dominant bits after passive error flag	TestIso_7_5_3	Completed	Yes	Yes		12
7	5	4		Passive state unchanged on further errors	TestIso_7_5_4	Completed	Yes	Yes		18
7	5	5		Passive error flag completion — Test case 2	TestIso_7_5_5	Completed	Yes	Yes		3
7	5	6		Form error in passive error delimiter	TestIso_7_5_6	Completed	Yes	Yes		6
7	5	7		Transition from active to passive ERROR FLAG	TestIso_7_5_7	Completed	Yes	Yes		4
Error counter management - Received Frame
7	6	1		REC increment on bit error in active error flag	TestIso_7_6_1	Completed	Yes	Yes		3
7	6	2		REC increment on bit error in overload flag	TestIso_7_6_2	Completed	Yes	Yes		3
7	6	3		REC increment when active error flag is longer than 13 bits	TestIso_7_6_3	Completed	Yes	Yes		1
7	6	4		REC increment when overload flag is longer than 13 bits	TestIso_7_6_4	Completed	Yes	Yes		1
7	6	5		REC increment on bit error in the ACK field	TestIso_7_6_5	Completed	Yes	Yes		1
7	6	6		REC increment on form error in CRC delimiter	TestIso_7_6_6	Completed	Yes	Yes		1
7	6	7		REC increment on form error in ACK delimiter	TestIso_7_6_7	Completed	Yes	Yes		1
7	6	8		REC increment on form error in EOF field	TestIso_7_6_8	Completed	Yes	Yes		3
7	6	9		REC increment on stuff error	TestIso_7_6_9	Completed	Yes	Yes		14
7	6	10		REC increment on CRC error	TestIso_7_6_10	Completed	Yes	Yes		3
7	6	11		REC increment on dominant bit after end of error flag	TestIso_7_6_11	Completed	Yes	Yes		1
7	6	12		REC increment on form error in error delimiter	TestIso_7_6_12	Completed	Yes	Yes		2
7	6	13		REC increment on form error in overload delimiter	TestIso_7_6_13	Completed	Yes	Yes		2
7	6	14		REC decrement on valid frame reception	TestIso_7_6_14	Completed	Yes	Yes		2
7	6	15		REC decrement on valid frame reception during passive state	TestIso_7_6_15	Completed	Yes	Yes		1
7	6	16		REC non-increment on last bit of EOF field	TestIso_7_6_16	Completed	Yes	Yes		1
7	6	17		REC non-increment on 13-bit length overload flag	TestIso_7_6_17	Completed	Yes	Yes		1
7	6	18		REC non-increment on 13-bit length error flag	TestIso_7_6_18	Completed	Yes	Yes		1
7	6	19		REC non-increment on last bit of error delimiter	TestIso_7_6_19	Completed	Yes	Yes		1
7	6	20		REC non-increment on last bit of overload delimiter	TestIso_7_6_20	Completed	Yes	Yes		1
7	6	21		REC non-decrement on transmission	TestIso_7_6_21	Completed	Yes	Yes		4
7	6	22		REC increment on form error at fixed stuff bit in FD frames	TestIso_7_6_22	Completed	Yes	Yes		14
7	6	23		REC non-increment on protocol exception in FD frames	TestIso_7_6_23	Completed	Yes	Yes		10
Bit timing Classical CAN format - Received Frame
7	7	1		Sample point test	TestIso_7_7_1	Completed	Yes	Yes		1
7	7	2		Hard synchronization on SOF reception	TestIso_7_7_2	Completed	Yes	Yes		PROP(N)+PH1(N)+PH2(N)+1	Warning
7	7	3		Synchronization when e > 0 and e ≤ SJW(N)	TestIso_7_7_3	Completed	Yes	Yes		SJW(N)
7	7	4		Synchronization when e > 0 and e > SJW(N)	TestIso_7_7_4	Completed	Yes	Yes		NTQ(N)-PH2(N)-SJW(N)-2
7	7	5		Synchronization when e < 0 and |e| ≤ SJW(N)	TestIso_7_7_5	Completed	Yes	Yes		SJW(N)
7	7	6		Synchronization when e < 0 and |e| > SJW(N)	TestIso_7_7_6	Completed	Yes	Yes		PH2(N) – SJW(N)
7	7	7		Glitch filtering test on positive phase error	TestIso_7_7_7	Completed	Yes	Yes		1
7	7	8		Glitch filtering test on negative phase error	TestIso_7_7_8	Completed	Yes	Yes		1
7	7	9	1	Glitch filtering test in idle state – single pulse	TestIso_7_7_9_1	Completed	Yes	Yes		1
7	7	9	2	Glitch filtering test in idle state – multiple pulses	TestIso_7_7_9_2	Completed	Yes	Yes		1
7	7	10		Non-Synchronization after a dominant sampled bit	TestIso_7_7_10	Completed	Yes	Yes		1
7	7	11		Synchronization when e < 0 and |e| ≤ SJW(N) at “ACK” bit position	TestIso_7_7_11	Completed	Yes	Yes		SJW(N)
Bit timing CAN FD frame format – Received Frame
7	8	1	1	Sample point test at “BRS” bit position	TestIso_7_8_1_1	Completed	Yes	Yes		2
7	8	1	2	Sample point test at “DATA” field	TestIso_7_8_1_2	Completed	Yes	Yes		2
7	8	1	3	Sample point test at “CRC delimiter” bit position	TestIso_7_8_1_3	Completed	Yes	Yes		2
7	8	2	1	Hard synchronization on “res” bit (delayed end of FDF)	TestIso_7_8_2_1	Completed	Yes	Yes		NTQ(N)-PH2(N)-SJW(N)-2
7	8	2	2	Hard synchronization on “res” bit (early end of FDF)	TestIso_7_8_2_2	Completed	Yes	Yes		1
7	8	3	1	Synchronization when e > 0 and e ≤ SJW(D) at ESI bit position	TestIso_7_8_3_1	Completed	Yes	Yes		SJW(D)	BRP = BRP_FD	Ambiguous
7	8	3	2	Synchronization when e > 0 and e ≤ SJW(D) at DATA field	TestIso_7_8_3_2	Completed	Yes	Yes		SJW(D)		Ambiguous
7	8	3	3	Synchronization when e > 0 and e ≤ SJW(D) at CRC delimiter bit position	TestIso_7_8_3_3	Completed	Yes	Yes		SJW(D)	Warning	Ambiguous + Typo
7	8	4	1	Synchronization when e > 0 and e > SJW(D) at ESI bit position	TestIso_7_8_4_1	Completed	Yes	Yes		NTQ(D)-PH2(D)-SJW(D)-2	BRP = BRP_FD	Ambiguous
7	8	4	2	Synchronization when e > 0 and e > SJW(D) at DATA field	TestIso_7_8_4_2	Completed	Yes	Yes		NTQ(D)-PH2(D)-SJW(D)-2		Ambiguous
7	8	4	3	Synchronization when e > 0 and e > SJW(D) at “CRC delimiter” bit position	TestIso_7_8_4_3	Completed	Yes	Yes		NTQ(D)-PH2(D)-SJW(D)-2		Ambiguous
7	8	5	1	Synchronization when e < 0 and |e| ≤ SJW(D) at “ESI” bit position	TestIso_7_8_5_1	Completed	Yes	Yes		SJW(D)		Ambiguous
7	8	5	2	Synchronization when e < 0 and |e| ≤ SJW(D) at “DATA” field	TestIso_7_8_5_2	Completed	Yes	Yes		SJW(D)		Ambiguous
7	8	5	3	Synchronization when e < 0 and |e| ≤ SJW(N) at “ACK” bit position	TestIso_7_8_5_3	Completed	Yes	Yes		SJW(D)		Ambiguous
7	8	6	1	Synchronization when e < 0 and |e| > SJW(D) at “ESI” bit position	TestIso_7_8_6_1	Completed	Yes	Yes		PH2(D) – SJW(D)		Ambiguous
7	8	6	2	Synchronization when e < 0 and |e| > SJW(D) at “DATA” field	TestIso_7_8_6_2	Completed	Yes	Yes		PH2(D) – SJW(D)		Ambiguous
7	8	6	3	Synchronization when e < 0 and |e| > SJW(N) at “ACK” bit position	TestIso_7_8_6_3	Completed	Yes	Yes		PH2(D) – SJW(D)		Ambiguous
7	8	7	1	Glitch filtering test on positive phase error at “res” bit position	TestIso_7_8_7_1	Completed	Yes	Yes		1
7	8	7	2	Glitch filtering test on positive phase error at “DATA” field	TestIso_7_8_7_2	Completed	Yes	Yes		1
7	8	7	3	Glitch filtering test on positive phase error at “ACK” bit position	TestIso_7_8_7_3	Completed	Yes	Yes		1
7	8	8	1	Glitch filtering test on negative phase error at “ESI” bit position	TestIso_7_8_8_1	Completed	Yes	Yes		1
7	8	8	2	Glitch filtering test on negative phase error at “DATA” field	TestIso_7_8_8_2	Completed	Yes	Yes		1		Error
7	8	8	3	Glitch filtering test on negative phase error at “ACK” bit position	TestIso_7_8_8_3	Completed	Yes	Yes		1
7	8	9	1	No synchronization after a dominant sampled bit at “BRS” bit position	TestIso_7_8_9_1	Completed	Yes	Yes		1
7	8	9	2	No synchronization after a dominant sampled bit at “DATA” field	TestIso_7_8_9_2	Completed	Yes	Yes		1
7	8	9	3	No synchronization after a dominant sampled bit at “CRC delimiter” bit position	TestIso_7_8_9_3	Completed	Yes	Yes		1
Valid Frame Format – Transmitted Frame
8	1	1		Identifier and number of data bytes test in base format	TestIso_8_1_1	Completed	Yes	Yes		125
8	1	2		Identifier and number of data bytes test in extended format	TestIso_8_1_2	Completed	Yes	Yes		125
8	1	3		Arbitration in base format frame	TestIso_8_1_3	Completed	Yes	Yes		11
8	1	4		Arbitration in extended format frame test	TestIso_8_1_4	Completed	Yes	Yes		62
8	1	5		Message validation	TestIso_8_1_5	Completed	Yes	Yes		1
8	1	6		Stuff bit generation capability in base format frame	TestIso_8_1_6	Completed	Yes	Yes		16
8	1	7		Stuff bit generation capability in extended frame	TestIso_8_1_7	Completed	Yes	Yes		13
8	1	8		Transmission on the third bit of intermission field after arbitration lost / Eighth bit of an error and overload delimiter	TestIso_8_1_8	Completed	Yes	Yes		8
Error Detection – Transmitted Frame
8	2	1		Bit error test in base format frame	TestIso_8_2_1	Completed	Yes	Yes		34
8	2	2		Bit error in extended format frame	TestIso_8_2_2	Completed	Yes	Yes		35
8	2	3		Stuff error test in base format frame	TestIso_8_2_3	Completed	Yes	Yes		74		ISO Error?
8	2	4		Stuff error test in extended frame format	TestIso_8_2_4	Completed	Yes	Yes		114		ISO Error?
8	2	5		Form error test	TestIso_8_2_5	Completed	Yes	Yes		23
8	2	6		Acknowledgement error	TestIso_8_2_6	Completed	Yes	Yes		4
8	2	7		Form field tolerance test for FD frame format	TestIso_8_2_7	Completed	Yes	Yes		2
8	2	8		Bit error at Stuff bit position for FD frame payload bytes	TestIso_8_2_8	Completed	Yes	Yes		1008
Error frame management – Transmitted frame
8	3	1		Error flag longer than 6 bit	TestIso_8_3_1	Completed	Yes	Yes		12
8	3	2		Transmission on the third bit of intermission field after error frame	TestIso_8_3_2	Completed	Yes	Yes		8
8	3	3		Bit error in error flag	TestIso_8_3_3	Completed	Yes	Yes		6
8	3	4		Form error in error delimiter	TestIso_8_3_4	Completed	Yes	Yes		3
Overload frame management - Transmitted Frame
8	4	1		MAC overload generation in intermission field	TestIso_8_4_1	Completed	Yes	Yes		4
8	4	2		Eighth bit of an error and overload delimiter	TestIso_8_4_2	Completed	Yes	Yes		6
8	4	3		Transmission on the third bit of intermission after overload frame	TestIso_8_4_3	Completed	Yes	Yes		2
8	4	4		Bit error in overload flag	TestIso_8_4_4	Completed	Yes	Yes		6
8	4	5		Form error in overload delimiter	TestIso_8_4_5	Completed	Yes	Yes		6
Passive error state – Transmitted Frame
8	5	1		Acceptance of active error flag overwriting passive error flag	TestIso_8_5_1	Completed	Yes	Yes		18
8	5	2		Frame acceptance after passive error frame transmission	TestIso_8_5_2	Completed	Yes	Yes		2
8	5	3		Acceptance of 7 consecutive dominant bits after passive error flag	TestIso_8_5_3	Completed	Yes	Yes		6
8	5	4		Reception of a frame during suspend transmission	TestIso_8_5_4	Completed	Yes	Yes		12
8	5	5		Transmission of a frame after suspend transmission — Test case 1	TestIso_8_5_5	Completed	Yes	Yes		4
8	5	6		Transmission of a frame after suspend transmission — Test case 2	TestIso_8_5_6	Completed	Yes	Yes		4
8	5	7		Transmission of a frame after suspend transmission — Test case 3	TestIso_8_5_7	Completed	Yes	Yes		4
8	5	8		Transmission of a frame without suspend transmission	TestIso_8_5_8	Completed	Yes	Yes		4
8	5	9		No transmission of a frame between the third bit of intermission field and / Eight bit of suspend transmission	TestIso_8_5_9	Completed	Yes	Yes		6
8	5	10		Bus-off state	TestIso_8_5_10	Completed	Yes	Yes		6
8	5	11		Bus-off recovery	TestIso_8_5_11	Completed	Yes	Yes		4		ISO Error
8	5	12		Completion condition for a passive error flag	TestIso_8_5_12	Completed	Yes	Yes		2
8	5	13		Form error in passive error delimiter	TestIso_8_5_13	Completed	Yes	Yes		2
8	5	14		Maximum recovery time after a corrupted frame	TestIso_8_5_14	Completed	Yes	Yes		4
8	5	15		Transition from active to passive ERROR FLAG	TestIso_8_5_15	Completed	Yes	Yes		4
Error counter management – Transmitted Frame
8	6	1		TEC increment on bit error during active error flag	TestIso_8_6_1	Completed	Yes	Yes		6
8	6	2		TEC increment on bit error during overload flag	TestIso_8_6_2	Completed	Yes	Yes		3
8	6	3		TEC increment when active error flag is followed by dominant bits	TestIso_8_6_3	Completed	Yes	Yes		2
8	6	4		TEC increment when passive error flag is followed by dominant bits	TestIso_8_6_4	Completed	Yes	Yes		10
8	6	5		TEC increment when overload flag is followed by dominant bits	TestIso_8_6_5	Completed	Yes	Yes		2		ISO Typo
8	6	6		TEC increment on bit error in data frame	TestIso_8_6_6	Completed	Yes	Yes		34
8	6	7		TEC increment on form error in a frame	TestIso_8_6_7	Completed	Yes	Yes		12
8	6	8		TEC increment on acknowledgement error	TestIso_8_6_8	Completed	Yes	Yes		4
8	6	9		TEC increment on form error in error delimiter	TestIso_8_6_9	Completed	Yes	Yes		12
8	6	10		TEC increment on form error in overload delimiter	TestIso_8_6_10	Completed	Yes	Yes		4
8	6	11		TEC decrement on successful frame transmission for TEC < 128	TestIso_8_6_11	Completed	Yes	Yes		2
8	6	12		TEC decrement on successful frame transmission for TEC > 127	TestIso_8_6_12	Completed	Yes	Yes		2
8	6	13		TEC non-increment on 13-bit long overload flag	TestIso_8_6_13	Completed	Yes	Yes		2
8	6	14		TEC non-increment on 13-bit long error flag	TestIso_8_6_14	Completed	Yes	Yes		4
8	6	15		TEC non-increment on form error at last bit of overload delimiter	TestIso_8_6_15	Completed	Yes	Yes		2
8	6	16		TEC non-increment on form error at last bit of error delimiter	TestIso_8_6_16	Completed	Yes	Yes		4		ISO Typo
8	6	17		TEC non-increment on acknowledgement error in passive state	TestIso_8_6_17	Completed	Yes	Yes		4
8	6	18		TEC increment after acknowledgement error in passive state	TestIso_8_6_18	Completed	Yes	Yes		4		ISO 1185 Ambiguity
8	6	19		TEC non-increment on stuff error during arbitration	TestIso_8_6_19	Completed	Yes	Yes		4		ISO Ambiguity
8	6	20		TEC non-decrement on transmission while arbitration lost	TestIso_8_6_20	Completed	Yes	Yes		4
8	6	21		TEC non-increment after arbitration lost and error	TestIso_8_6_21	Completed	Yes	Yes		2		ISO Error!
Bit timing – Transmitted Frame
8	7	1		Sample point test	TestIso_8_7_1	Completed	Yes	Yes		NTQ(N)-2
8	7	2		Hard synchronization on SOF reception before sample point	TestIso_8_7_2	Completed	Yes	Yes		NTQ(N)-2
8	7	3		Hard synchronization on SOF reception after sample point	TestIso_8_7_3	Completed	Yes	Yes		NTQ(N)-3
8	7	4		Synchronization when e < 0 and |e| ≤ SJW(N)	TestIso_8_7_4	Completed	Yes	Yes		MIN(SJW(N), PH2(N)
8	7	5		Synchronization for e < 0 and |e| > SJW(N)	TestIso_8_7_5	Completed	Yes	Yes		PH2(N) – SJW(N)
8	7	6		Glitch filtering test on negative phase error	TestIso_8_7_6	Completed	Yes	Yes		NTQ(N)-3
8	7	7		Non-synchronization on dominant bit transmission	TestIso_8_7_7	Completed	Yes	Yes		NTQ(N)-4
8	7	8		Synchronization before information processing time	TestIso_8_7_8	Completed	Yes	Yes		NTQ(N)-2
8	7	9		Synchronization after sample point while sending a dominant bit	TestIso_8_7_9	Completed	Yes	Yes		NTQ(N)-3		ISO Error
Bit timing CAN FD frame format – Transmitted Frame
8	8	1	1	Sample point test at “res” bit	TestIso_8_8_1_1	Completed	Yes	Yes		NTQ(N)-2
8	8	1	2	Sample point test at BRS bit	TestIso_8_8_1_2	Completed	Yes	Yes		NTQ(N)-2	BRP > 2
8	8	1	3	Sample point test in DATA field	TestIso_8_8_1_3	Completed	Yes	Yes		2 * NTQ(D)-4	BRP_FD > 2
8	8	1	4	Sample point test at CRC delimiter bit	TestIso_8_8_1_4	Completed	Yes	Yes		NTQ(D)-2	BRP_FD > 2
8	8	2	1	No secondary sample point test at “res” bit	TestIso_8_8_2_1	Completed	Yes	Yes		4
8	8	2	2	No secondary sample point test at BRS bit	TestIso_8_8_2_2	Completed	Yes	Yes		4
8	8	2	3	Secondary sample point test in DATA field	TestIso_8_8_2_3	Completed	Yes	Yes		4	BRP_FD > 2
8	8	2	4	Secondary sample point test at end of data phase	TestIso_8_8_2_4	Completed	Yes	Yes		4	BRP_FD > 2	ISO Amiguity
8	8	3	1	No synchronization within data phase bits when e < 0; |e| ≤ SJW(D) (BRS)	TestIso_8_8_3_1	Completed	Yes	Yes		1	BRP_FD > 2
8	8	3	2	No synchronization within data phase bits when e < 0; |e| ≤ SJW(D) (DATA field)	TestIso_8_8_3_1	Completed	Yes	Yes		1	BRP_FD > 2
8	8	4	1	Glitch filtering test on negative phase error within FD frame at “ESI” bit position	TestIso_8_8_4_1	Completed	Yes	Yes		1	BRP_FD > 2
8	8	4	2	Glitch filtering test on negative phase error within FD frames at “DATA” field position	TestIso_8_8_4_2	Completed	Yes	Yes		1	BRP_FD > 2	ISO Error
8	8	5	1	No synchronization on dominant bit transmission in FD frame at “ESI” bit position	TestIso_8_8_5_1	Completed	Yes	Yes		1
8	8	5	2	No Synchronization on dominant bit transmission in FD frames at “DATA” field position	TestIso_8_8_5_2	Completed	Yes	Yes		1
Error counter management – Bidirectional Frame
9	6	1		REC unaffected when increasing TEC	TestIso_9_6_1	Completed	Yes	Yes		17
9	6	2		TEC unaffected when increasing REC	TestIso_9_6_2	Completed	Yes	Yes		258